## Sheet1
Topic # | Topic Description | Raised By | References | Priority | Status | Date Raised | Date Closed | Investigation Status | Outcome/Comments | Key
1 | Refer to Xoserve as CDSP | Eon | Consultation Response 2018_2 |  | Closed |  |  |  | AUGS Updated and references will be to CDSP going forward | Closed Topic from a previous AUG year
2 | AUGS References to SSP/LSP | Eon | Consultation Response 2018_3 |  | Closed |  |  |  | References to SSP/LSP in AUGS are correct within the context they are used | Topic investigated but requiring further analysis
3 | UIG/UG Terminology | Eon | Consultation Response 2018_4 |  | Closed |  |  |  | AUGS updated to include more clarification on terminology used | New Topic or Topic not resolved and carried forward to next year
4 | Pressure & Temperature Corrections | Eon | Consultation Response 2018_5 |  | Closed |  |  |  | Issue closed - broken down into a number of smaller issues. See 25-30 below | New Topic for assessment
5 | Non-compliance with mandatory AMR >04B | Eon | Consultation Response 2018_6 |  | Closed |  |  |  | Use of AMR for >04B is a license condition which the AUGE assumes is largely met. No reliable dataset exists for the presence of AMR devices
6 | Explanation of cubic smoothing of factors | Eon | Consultation Response 2018_7, AUGS for 2018/19 |  | Closed |  |  |  | Description included in AUGS for 2018/19
7 | Meter read spacing for consumption calculation | Eon | Consultation Response 2018_7, AUGS for 2018/19 |  | Closed |  |  |  | Justification for current approach detailed in consultation responses and AUGS for 2018/19
8 | More Detailed Theft Analysis | Eon, Corona Energy, ICoSS & British Gas | Consultation Responses 2018_9, 2018_14, 2018_15, 2018_17 & 2018_23 | H | Open | 2018-03-01 |  | Ongoing data collection and analysis | 2019/20: Further analysis being undertaken. Additional data request from TRAS approved. 2018/19: A proposed methodology has been documented separately to the AUGS. TRAS outcome data (leads investigated) and SPAA theft report received but TRAS data request did not include ETTOS leads and TRAS Qualified Outliers. Not possible to use proposed theft methodology in its entirety. Issue therefore left open for further analysis in 2019/20
9 | References to Theft Data | Eon | Consultation Response 2018_10 |  | Closed |  |  |  | References to TRAS have been corrected throughout AUGS
10 | Theft Split in SPAA Report. Concern that SPAA data is being split by product class and this is not described in AUGS | Eon | Consultation Response 2018_11 |  | Closed |  |  |  | SPAA data is only used as a Total in detected theft calculation and no split by product class is assumed
11 | Use of Site Specific Correction Factors in AUGE calculations | Eon | Consultation Response 2018_12 |  | Closed |  |  |  | AUGE confirmed that consumption calculations use site specific factors
12 | Concerns over AUGE Independence | Eon | Consultation Response 2018_13 |  | Closed |  |  |  | AUGE is mindful of feedback and is keen to work with industry to dispel this perception
13 | Shrinkage error is the responsibility of the shrinkage forum | Corona Energy & ICoSS | Consultation Responses 2018_16 & 2018_20 |  | Closed |  |  |  | Noted
14 | Theft from PC2 (DMV/DME sites previously). Prior to Nexus DME/DMV sites were allocated no UG. Is it correct for these same sites to be allocated UIG when they move to PC2? | ICoSS | Consultation Response 2018_18 | M | Closed |  |  |  | For analysis 2018/19- analysis complete.
15 | SMART/AMR population estimates. Data used by the AUGE does not include all AMR devices (some AMRs on sites <04B which aren't reported via BEIS) | ICoSS | Consultation Response 2018_19 |  | Closed |  |  |  | ICoSS provided additional data which has been used
16 | Impact of Nexus DM Errors | British Gas | Consultation Response 2018_21 |  | Closed |  |  |  | DM errors experienced during Nexus transition will not impact the historic (pre-Nexus) data used by the AUGE for 2018/19
17 | Allocation of Balancing Factor to DM Sites. Although there have been no recorded incidents of theft from PC1 sites, there are other potential ways that PC1 sites can contribute to UG e.g. open bypass valves | British Gas | Consultation Response 2018_22 |  | Closed |  |  |  | There is a lack of evidence to support the allocation of the balancing factor to PC1 sites
18 | Smart Meter Population. Use of a mid-point estimate of population would be more appropriate rather than start of year. The number of meters reported to BEIS does not include smaller suppliers and pre-SMETs aren't included in BEIS stats | British Gas | Consultation Response 2018_24 |  | Closed |  |  |  | Methodology updated to use a mid-year figure and a trend in installation rate for each future quarter. Data from small suppliers provided by ICoSS is now included. Pre-SMETs meters are included where these have been identified from the meter information provided by the CDSP
19 | Uniformly Allocable Sources of UG. A generic term for as yet unidentified sources of UG should be included in the methodology | British Gas | Consultation Response 2018_25 |  | Closed |  |  |  | A term has been added to the methodology for UG which will be split based on throughput but this is initially set to zero
20 | Statistical Housekeeping - request for information on confidence intervals | British Gas | Consultation Response 2018_26 |  | Closed |  |  |  | The production of confidence intervals for UG is complex and is outside the AUGE's remit
21 | Improved Replacement Values in Consumption Calculation | DNV GL | AUG TWG Meeting Minutes, 10 Aug 2018 | M | Closed | 2018-08-10 |  |  | For analysis 2018/19- analysis complete.
22 | Is a single table appropriate for allocating UIG? Should the AUGE be considering how to apportion UIG on the day as well as at line in the sand | Gazprom | AUG TWG Meeting Minutes, 10 Aug 2018 |  | Closed | 2018-08-10 |  |  | No action required. The remit of the AUGE is to create a single table of factors as per UNC to apportion UIG.
23 | Changes to NDM algorithm parameters e.g. scaling factors for ALPs and DAFs | British Gas | AUG TWG Meeting Minutes, 10 Aug 2018 |  | Closed | 2018-08-10 |  |  | Changes to NDM algorithm will affect UIG on the day but this will ultimately be reconciled using meter reads. As the factors created by the AUGE aim to correctly apportion UG at line in the sand, changes to the algorithm are largely irrelevant. The exception to this is the use of the NDM algorithm to calculate annual consumptions based on meter reads and correct these to SN conditions. In this case, unscaled parameter values will be used as the scaling is aimed at reducing initial UIG levels. More detail to be provided in AUGS
24 | Shrinkage error. The AUGE should be estimating the error in the shrinkage estimate | British Gas | AUG TWG Meeting Minutes, 10 Aug 2018 |  | Closed | 2018-08-10 |  |  | No further action required. Estimation of shrinkage is explicitly outside the scope of the AUGE as it is the responsibility of GTs who have a license condition to accurately calculate it. The methodology does include a term for CSEP shrinkage which is not currently estimated at all.
25 | Use of static correction factors for volume conversion. In order to get an accurate conversion from volume to energy, correction factors should ideally be based on local weather conditions (pressure and temperature). Are the currently assumed average values appropriate or are they causing UIG? | Scottish Power | AUG TWG Meeting Minutes, 10 Aug 2018 | H | Open | 2018-08-10 |  | Awaiting results of gas meter temperature study | 2019/20: Further analysis planned if gas meter temperature study completed. 2018/19: Analysis complete. See AUGS for detail. Investigation to continue in 2019/20.
26 | Incorrect site specific correction factors | Scottish Power | AUG TWG Meeting Minutes, 10 Aug 2018 | M | Closed | 2018-08-10 |  |  | Analysis complete. Insignificant contribution to permanent UIG
27 | Use of standard correction factors for sites >04B | Scottish Power | AUG TWG Meeting Minutes, 10 Aug 2018 | M | Closed | 2018-08-10 |  |  | Analysis complete. Estimated annual contribution to UIG of 136GWh
28 | Accuracy of volume converters | Scottish Power | AUG TWG Meeting Minutes, 10 Aug 2018 | L | Closed | 2018-08-10 |  |  | Analysis complete. Insignificant contribution to permanent UIG
29 | Use of non-standard correction factors for sites <04B. Currently only sites >04B are required to have site specific correction factors. Is the assumption of average altitude of 66m (the basis for the standard factors) contributing to UG? | DNV GL | AUG TWG Meeting Minutes, 10 Aug 2018 | M | Closed | 2018-08-10 |  |  | Analysis complete. Insignificant contribution to permanent UIG
30 | Effect of inaccurate CV on volume to energy conversion | DNV GL | AUG TWG Meeting Minutes, 10 Aug 2018 | M | Closed | 2018-08-10 |  |  | Analysis complete. No bias present
31 | Estimates of product class populations as movement between classes is not linear. Can AUGE track rate of change? | British Gas | AUG TWG Meeting Minutes, 10 Aug 2018 | M | Closed | 2018-08-10 |  |  | Analysis complete.
32 | Why does allocated UIG change significantly for a site when it changes product class? | Orsted | AUG TWG Meeting Minutes, 10 Aug 2018 | L | Closed | 2018-08-10 |  |  | Factors apportion UIG based on average behaviour of product class and do not represent the behaviour of any individual site within that product class. The granularity of the factors (by EUC and Product Class) are specified in UNC. An explanation has been included within the AUGS
33 | What is the level of permanent UIG post-Nexus? Can the AUGE analyse reconciliation data and provide a view? | SSE | AUG TWG Meeting Minutes, 10 Aug 2018 | M | Open | 2018-08-10 |  | Ongoing monitoring | 2019/20: AUGE will continue to monitor and provide updates as required. Regular updates are also provided by Xoserve at https://www.xoserve.com/services/issue-management/unidentified-gas-uig/#useful-links 2018/19: The CDSP provided reconciliation data post-Nexus for the AUGE to analyse. However, Xoserve have already presented results of analysis of this data on 13 Nov 2018 showing that reconciliation has reduced average UIG from 4.65% at allocation to 4% at reconciliation (after 15 months). Although 4% is higher than the AUGE's estimate of 1%, this is not a like-for-like comparison. The AUGE's estimate is based on historic data which (for most years) includes all reconciliations to line in the sand. It is also an average over a number of years based on SN conditions. No further analysis on reconciliations is planned this AUGE year, but the AUGE has been discussing options with Xoserve for a more detailed analysis with the aim of identifying the source of the discrepancy. Further analysis will fall into the 2019/20 AUGE year. More recent Xoserve analysis up to November 2018 (18 months) now shows Initial UIG at 3.8%, dropping to 3.5% post-reconciliation. Xoserve are providing monthly updates - April 2019 update can be found at https://www.xoserve.com/media/4068/uig-tracking-april-30-2019.pdf Xoserve continue to provide updates which show reducing levels of UIG. For July 2019 (data up to May 2019), UIG was at 2.46% pre-reconciliation and 3.18% post-reconciliation based on all pre-Nexus data
34 | Discrepancy between closing and opening meter reads on supplier change | DNV GL | AUG TWG Meeting Minutes, 10 Aug 2018 |  | Closed | 2018-08-10 |  |  | No action required. The AUG TWG considered that this was not a source of UG and is correctly handled through ISD (Inter-Shipper Dispute) process
35 | Potential for UG as a result of meter change e.g. failure to supply opening read, read rejection etc | DNV GL | AUG TWG Meeting Minutes, 10 Aug 2018 | L | Open | 2018-08-10 |  | Awaiting data | 2019/20: Data requested for further analysis 2018/19: Sample data provided by CDSP. Analysis started and a number of issues raised with CDSP. CDSP have confirmed that the AUGE are missing some meter read data which will be provided. Analysis will continue in 2019/20 AUG year.
36 | Incrementing Reads for Isolated Supply Points | DNV GL | DSC Change Proposals XRN4622 and XRN4645 | L | Closed | 2018-08-01 |  |  | UIG taskforce has assessed this and concluded that known sites contribute around 0.006% of total throughput and their investigations into unknown sites is ongoing. No further analysis is therefore planned for this year
37 | Discrepancies between converted and unconverted meter reads | DNV GL | DSC Change Proposal XRN4621 | L | Open | 2018-08-01 |  |  | New. Awaiting more information from CDSP. Believe any UIG will be temporary
38 | Inadequacies in the CWV formula | UIG Workgroup | UIG Task Force Progress Report, ChMC 10th October 2018 |  | Closed | 2018-10-10 |  |  | Could impact consumption calculations as CWV is used in SN correction post-Nexus (via WCF). However, currently all data used in consumption calculations are from pre-Nexus. CWV is also being assessed by the UIG taskforce and Mod0659 has been raised to provide improvements to CWV
39 | Accuracy of NDM algorithm | UIG Workgroup | UIG Task Force Progress Report, ChMC 10th October 2018 |  | Open | 2018-10-10 |  | Ongoing monitoring | 2019/20: AUGE will monitor as this may impact methodology 2018/19: This mostly impacts levels of temporary UIG and is therefore not relevant to the calculation of UIG factors. However, it is noted that it will also impact the AUG Expert consumption calculations as the algorithm is used in SN correction and to split consumption into gas years. Issues with volume/energy conversion (#25-#30) will directly affect the accuracy of the NDM algorithm and the AUG Expert has made the industry/UIG taskforce aware of this. This is being investigated further by the taskforce and information will continue to be shared. No further analysis is planned by the AUG Expert in 2018/19.
40 | Use of estimates for DM sites | UIG Workgroup | UIG Task Force Progress Report, ChMC 10th October 2018 |  | Closed | 2018-10-10 |  |  | Has been considered previously by AUGE and discounted as a source of permanent UIG. It is assumed that all DM sites will be accurately reconciled before line in the sand
41 | Accuracy/out-of-date AQs for class 3&4 sites | UIG Workgroup | UIG Task Force Progress Report, ChMC 10th October 2018 | L | Closed | 2018-10-10 |  |  | This mostly impacts levels of temporary UIG and is therefore not relevant to the calculation of UIG factors. However it will impact historic consumption estimates of CSEPs which are based on AQs (no other data available pre-Nexus). Also used for validation of calculated consumptions. AQs will be affected by volume/energy conversion issues (#25-#30) and the AUG Expert has made the industry/UIG taskforce aware of this. This is being investigated further by the taskforce and information will continue to be shared. No further analysis is planned by the AUG Expert this year.
42 | Low take-up of WAR band EUCs | UIG Workgroup | UIG Task Force Progress Report, ChMC 10th October 2018 | TBD | Closed | 2018-10-10 |  |  | This mostly impacts initial allocation and therefore levels of temporary UIG. It is therefore not relevant to the calculation of UIG factors. There will be an impact on the AUG Experts consumption estimates as calculations are done on an EUC basis. As this issue is under investigation by the UIG taskforce, no further investigation is planned for this year.
43 | Suitability of NDM sample site data | UIG Workgroup | UIG Task Force Progress Report, ChMC 10th October 2018 |  | Closed | 2018-10-10 |  |  | NDM sample data will affect allocation. Assuming most sites are reconciled before line in the sand, the contribution to permanent UIG will be negligible. However, it should be noted that the NDM sample data will contain an error due to imperfect volume conversion (mainly due to fixed temperature assumption). This is covered separately in Issue #25
44 | Sites on CSEPs not recorded on CDSP system | UIG Workgroup | UIG Task Force Progress Report, ChMC 10th October 2018 |  | Closed | 2018-10-10 |  |  | This has already been assessed and is accounted for in the AUG Methodology
45 | CSEP-LDZ mapping | UIG Workgroup | UIG Task Force Progress Report, ChMC 10th October 2018 |  | Closed | 2018-10-10 |  |  | This will result in UIG appearing in the incorrect LDZ. As AUG factors are not LDZ specific, there should be no net effect from the point of view of calculating permanent national UIG and therefore the UIG factors
46 | LDZ Measurement Errors | UIG Workgroup | UIG Task Force Progress Report, ChMC 10th October 2018 |  | Closed | 2018-10-10 |  |  | This has already been considered by the AUGE and is included within the current methodology
47 | Unregistered/Shipperless Sites | UIG Workgroup | UIG Task Force Progress Report, ChMC 10th October 2018 |  | Closed | 2018-10-10 |  |  | This has already been considered by the AUGE and is included within the current methodology
48 | IGT Shrinkage | UIG Workgroup | UIG Task Force Progress Report, ChMC 10th October 2018 |  | Closed | 2018-10-10 |  |  | This has already been considered by the AUGE and is included within the current methodology
49 | Accuracy of NDM read estimates | UIG Workgroup | UIG Task Force Progress Report, ChMC 10th October 2018 | L | Closed | 2018-10-10 |  |  | Analysis complete. Consumption calculation does not distinguish between actual and estimated reads. On average, 0.05% of reads used are estimated and >98% of these are in 01B. The impact will be negligible.
50 | Live sites in Dead status | UIG Workgroup | UIG Task Force Progress Report, ChMC 10th October 2018 | L | Closed | 2018-10-10 |  |  | Xoserve have confirmed that the number of sites involved is small and their investigations are ongoing. No further analysis is therefore planned for this year
51 | Inaccuracy of metering equipment at end consumer property | UIG Workgroup | UIG Task Force Progress Report, ChMC 10th October 2018 |  | Closed | 2018-10-10 |  |  | This has already been considered by the AUGE and is included within the current methodology
52 | Incorrect or missing data on the supply point register | UIG Workgroup | UIG Task Force Progress Report, ChMC 10th October 2018 |  | Closed | 2018-10-10 |  |  | This is under investigation by the UIG taskforce. The AUG Expert plans no analysis this year but will monitor taskforce findings
53 | Supplier going out of business | DNV GL |  |  | Closed | 2018-10-01 |  |  | According to BBC news, 6 suppliers have gone out of business so far in 2018. In these cases, Ofgem appoints a new supplier. Xoserve has confirmed that these sites will not contribute to permanent UIG
54 | Incorrect customer information e.g. address | DNV GL | SGN Pre-pay Presentation on JoT, 22 Feb 2019 http://www.gasgovernance.co.uk/280119 |  | Open | 2019-02-27 |  | Awaiting data & Skype call | SGN have highlighted a number of issues relating to pre-payment meters but similar issues e.g. incorrect address data could affect all meters. This should already be covered by existing Shipperless/Unregistered analysis. Skype call arranged with SGN to discuss further.
55 | Creation of New End User Categories | Gazprom | XRN4665 – Creation of New End User Categories |  | Open | 2019-03-01 |  | On hold | Discussed when UNC Mod was first raised and considered unnecessary to break down UIG factors to sub-EUC level. In light of theft being predominantly from ETM pre-payment meters, this should be reconsidered. No impact on UIG factors currently. Data has been requested at new EUC level to allow analysis if required
56 | Assess correlation between detected theft levels & UIG | Npower | UNCC AUG Sub-Committee meeting minutes, 15 March 2019 | L | Closed | 2019-03-15 |  |  | John Welch suggested that the AUGE should look for additional evidence that the Balancing Factor is composed of mostly undetected theft. He suggested looking at the relationship between levels of detected theft and UIG by LDZ. Analysis published on JoT, May 2019
57 | Use of flat shrinkage profile | British Gas | AUGS 2019-20 British Gas - DNV GL Comments.pdf |  | Closed | 2019-01-21 | 2019-07-24 |  | Subject to agreement that this does not contravene AUG framework/UNC. Discussed at UNCC Sub-committee meeting, 24 July 2019 and suggested that this should first be raised at shrinkage forum
58 | More detailed analysis of meter locations | Shipper1 | AUGS 2019-20 Shipper1 - DNV GL Comments.pdf | L | Open | 2019-01-21 |  | Analysis ongoing | Analysis will look at meter location by EUC/Product class. Initial results included in August 2019 monthly report
59 | Review of methodology to estimate CSEP consumption (used to estimate total UG and therefore balancing factor) | DNV GL | AUG Sub-committee of UNCC, Introductory Meeting for 2019/20 | M | Open | 2019-07-24 |  | Awaiting data for initial analysis | When calculating total consumption and UIG for historic years to estimate the balancing factor, aggregate CSEP data (only AQ and SP count) are used. Post-Nexus, more detailed CSEP information is available. Sufficient data may now exist for a more robust estimation of CSEP consumption.
60 | Investigate use of temperature data from volume converters | Orsted | AUG Sub-committee of UNCC, Introductory Meeting for 2019/20 |  | Open | 2019-07-24 |  | Awaiting data for initial analysis | Initially expected to use corrected/uncorrected reads but having received sample data this may not be possible. May need to request temperature data separately.
61 | Investigate use of corrected vs uncorrected reads to assess temperature effects | Orsted | AUG Sub-committee of UNCC, Introductory Meeting for 2019/20 |  | Open | 2019-07-24 |  | Analysis ongoing | Sample of corrected and uncorrected reads received from CDSP for 1 LDZ. Initial assessment ongoing.
62 | Meter Bypasses | Scottish Power | AUG Sub-committee of UNCC, Introductory Meeting for 2019/20 |  | Closed | 2019-07-24 | 2019-07-24 |  | This has been considered previously. There are processes in place for reporting and correcting for unmetered gas flows.