## Summary
Data Request ID | Contributor | Data Item | Data Item Description | Priority Rating | Source | Request Date | Expected Date | Status | Received | Validated | Comments | Updated data request Refresh Request (Y/N) | Updated data request Refresh Date | Expected date2 | Monthly updated if available (Y/N) | Update Received | Update comments
1 | Theft | Shipper Theft Data | Details of theft provided to Xoserve within CMS | H | Xoserve | 2020-06-30 | 2020-07-27 | Valid | Y | Y |  | Y | 2020-09-18 | 2020-10-01 | Y | Y
2 | Theft | TRAS Outcome File Data | The data outcome from TRAS | H | Xoserve (TRAS) | 2020-06-30 | 2020-07-27 | Valid | Y | Y | Latest data up to September 2019. Data refresh October 2020 | Y | 2020-09-18 | 2020-10-08 | N | Y | Shipper details not included
3 | Theft | TRAS Suspected Thefts | ETTOS Data | H | Xoserve (TRAS) | 2020-06-30 | 2020-07-27 | In Query | Y |  | Have queried this data as there were duplicates and date was 1899.
4 | Unregistered Shipperless | Snapshot files (including MPR details) | Monthly Snapshot files | M | Xoserve | 2020-06-30 | 2020-07-27 | In Query | Y | N | MPRNs are stored on multiple tabs. E.G there re orphaned ones and legitimate ones. How could this be possible? | Y | 2020-09-18 | 2020-10-05 | Y | In Query - We identified a number of duplicates on this
5 | Unregistered Shipperless | Gas Safety Regulations visit data | Details of Gas Safety Regulation Visits | M | Xoserve | 2020-06-30 | 2020-07-27 | Valid | Y | Y |  | N
6 | Unregistered Shipperless | Mod 0410A supporting data | Supporting data from the UNC Mod 0410A: Responsibility for gas off-taken at Unregistered Sites following New Network Connections. | L | Xoserve | 2020-06-30 | 2020-08-17 | No Longer required
7 | Unregistered Shipperless | Connection details for orphaned sites | Details of connections for Orphaned sites | M | Xoserve | 2020-06-30 | 2020-07-27 | Valid | Y | Y |  | Y | 2020-09-18 | 2020-10-05 | Y | N
8 | IGT Unknown Projects | Not currently planned for investigation
9 | Consumption Meter Errors | Meter Capacity report | A report providing the capacity of meter | M | Xoserve | 2020-06-30 | 2020-08-03 | Valid | Y | Y | Duplicates are down to multi metered supply points | N
10 | Meter Errors at LDZ input | Meter Errors | This file provides details of the meter errors that have taken place and their associated energy | M | Xoserve | 2020-06-30 | 2020-08-03 | Valid | Y | Y |  | N
11 | Meter Errors at LDZ input | Measurement Error Register | The register of the Measurement Errors held on the Joint Office Website | M | Joint Office website | n/a | n/a |  | Y | Y |  | n/a
12 | IGT Shrinkage | Main Length | Details of the length of main and the total number of end users | H | IGTs | 2020-08-25 | 2020-10-01 | Awaiting info |  |  |  | n/a |  |  |  | N
13 | IGT Shrinkage | Leakage Rates | Leakage rates from the NLT | H | Public Domain | n/a | n/a |  |  |  |  | n/a
14 | IGT Shrinkage | IGT Sites | Number and associated AQ of sites on IGTs | M | Xoserve | 2020-06-30 | 2020-08-03 | Valid | Y | Y |  | N
15 | Atmospheric Pressure Assumption | Historical Pressure Information | Historical Pressure information by Weather Station | M | Xoserve | 2020-06-30 | 2020-08-03 | Valid | Y | Y | Received from DNV | N
16 | Atmospheric Pressure Assumption | Sites with volume conversion equipment fitted | A report providing information for sites that have volume conversion equipment fitted | M | Xoserve | 2020-06-30 | 2020-08-03 | Valid | Y | Y |  | Y | 2020-09-18 | 2020-10-05 | N | Y
17 | Average Temperature Assumption | Meter Location | Snapshot of the meter location split by EUC band | M | Xoserve | 2020-06-30 | 2020-08-03 | Valid | Y | Y |  | N
18 | Average Temperature Assumption | Gas Temperature Data | Gas Temperature Data From DMTS & ICTS | M | DNV | 2020-06-15 | 2020-06-15 | Valid | Y | Y |  | N
19 | No meter read at line in the sand | Sites with no reads after April 2018 | Details of the sites with no actual read after April 2018 | H | Xoserve | 2020-06-30 | 2020-07-27 | Valid | Y | Y |  | Y | 2020-09-18 | 2020-10-01 | Y | Y | A few site differences in query
20 | No meter read at line in the sand | Change in AQ since June 2017 | A report by class and EUC of the change in rolling AQ | H | Xoserve | 2020-06-30 | 2020-07-27 | Valid | Y | Y |  | Y | 2020-09-18 | 2020-10-01 | Y | Y
21 | Large sites with incorrect correction factors | Site details | Correction factors for all sites in EUC04 and above | M | Xoserve | 2020-06-30 | 2020-08-03 | Valid | Y | Y |  | Y | 2020-09-18 | 2020-10-05 | N | Y
22 | Large sites with incorrect correction factors | Correction Factor Changes | Changes to correction factor within year | L | Xoserve | Not required as data refresh requested | [5 empty] | n/a
23 | CV Shrinkage | Not currently planned for investigation | [9 empty] | n/a
24 | Meter Exchanges | Not currently planned for investigation | [9 empty] | n/a
25 | General Industry Information | Market summary report | A snapshot report of the number of Live sites and associated AQ | M | Xoserve | 2020-06-30 | 2020-08-03 | No Longer required | n/a |  | no longer needed | n/a
26 | General Industry Information | Future class change | A report of any known future class changes indicated by Shippers | M | Xoserve | 2020-06-30 | 2020-08-03 | No report exists | n/a |  | no report exists | n/a
27 | General Industry Information | Allocation | Allocation by LDZ | M | Xoserve | 2020-06-30 | 2020-08-03 | Valid | Y | Y | Xoserve are confirming details within the file | Y | 2020-09-18 | 2020-10-05 | N
28 | General Industry Information | Throughput | Daily Total throughput, DM allocation and UIG by EUC | M | Xoserve | 2020-06-30 | 2020-08-03 | Valid | Y | Y |  | Y | 2020-09-18 | 2020-10-05 | N | Y
29 | General Industry Information | Daily Allocation Factor | The daily Allocation factors applied to NDM sites | M | Xoserve | 2020-06-30 | 2020-08-03 | Valid | Y | Y |  | N
30 | General Industry Information | Reconciliation | Monthly report of the reconciliations since Nexus go live | M | Xoserve | n/a |  |  | Y | Y |  | n/a
31 | General Industry Information | Additional reconciliation information | Percentage of DM energy reconciled to actual read or better estimate based on actual read | M | Xoserve | 2020-06-30 | 2020-08-03 | No report exists
32 | Other | AMR Date |  | L | ICOSS | TBC |  | Data not currently required |  |  |  | n/a
33 | Other | Smart Meter Data |  | M | Public domain | n/a | n/a |  |  |  |  | n/a
Additional reports in updated request
34 | Unregistered Shipperless | Connection details for Shipperless sites | Details of connections for shipperless sites | M | Xoserve | n/a | n/a | n/a | n/a | n/a |  | Y | 2020-09-18 | 2020-10-05 | Y | Y
35 | Consumption Meter Errors | Meter Error Report | Details of previous faulty meters | M | Xoserve | n/a | n/a | n/a | n/a | n/a |  | Y | 2020-09-18 | 2020-10-05 | N | Y
36 | Consumption Meter Errors | Meter type and age report | Meter Type by EUC, Class and installation year | M | Xoserve | n/a | n/a | n/a | n/a | n/a |  | Y | 2020-09-18 | 2020-10-05 | N | Y
37 | No meter read at line in the sand | Must read report | Details of the must reads carried out on sites without reads | H | Xoserve | n/a | n/a | n/a | n/a | n/a |  | Y | 2020-09-18 | 2020-10-01 | N | Y
38 | No meter read at line in the sand | AQ corrections | Details of the AQ Corrections carried out on sites without reads | H | Xoserve | n/a | n/a | n/a | n/a | n/a |  | Y | 2020-09-18 | 2020-10-01 | N | Y
39 | No meter read at line in the sand | Read rejections | Details of the read rejections carried out on sites without reads | H | Xoserve | n/a | n/a | n/a | n/a | n/a |  | Y | 2020-09-18 | 2020-10-01 | N | Y
40 | General Industry Information | Shipper supply proportions | Proportion of sites and AQ registered to a particular Shipper | M | Xoserve | n/a | n/a | n/a | n/a | n/a |  | Y | 2020-09-18 | 2020-10-05 | Y | N
41 | General Industry Information | Reconciliation Percentages | Historical reconciliation percentages by month for each EUC | M | Xoserve | n/a | n/a | n/a | n/a | n/a |  | Y | 2020-09-18 | 2020-10-05 | N | N
42 | Consumption Meter Errors | Annual in-service testing | In service testing of domestic sized meters | H | BEIS - Office for Product Safety and Stadard | n/a | n/a | n/a | n/a | n/a |  | Y | 2020-09-17 | 2020-10-01 | N | Y | Received three years worth of data